## Task Tracker
ID | Task Name | Task Type | Status | Start Date | Due Date | Estimated Time | Time Spent | % Completion
74543 | Boiler Plate Changes | Main Task | Done | 4572300% | 4572300% | 2 | 2 | 100%
63179 | Boiler NextJs Application | Subtask | Done | 4572300% | 4572300% | 1 | 1 | 100%
16413 | Connect with GitHub Repo | Subtask | Done | 4572300% | 4572300% | 1 | 1 | 100%
31673 | Landing Page | Main Task | In Progress | 4572400% | 4572500% | 6 | 0 | 0%
47536 | Add a landing page | Subtask | Done | 4572400% | 4572500% | 2 | 2 | 100%
20414 | Define color scheme for the application | Subtask | In Progress | 4572400% | 4572500% | 4 | 2 | 50%
36586 | Navbar Development | Main Task | New | 4572500% | 4572500% | 8 | 0 | 0%
84810 | Adding Application Tab | Subtask | New | 4572500% | 4572500% | 4 | 0 | 0%
47353 | Dashboard Tab | Subtask | New | 4572500% | 4572500% | 4 | 0 | 0%
67922 | Create State Management Layer | Main Task | New | 4572600% | 4572700% | 8 | 0 | 0%
16043 | Implement Zustand State Management | Subtask | New | 4572600% | 4572700% | 2 | 0 | 0%
91193 | Create Stores [Form Data, Dashboard Data, UserData] | Subtask | New | 4572600% | 4572700% | 6 | 0 | 0%
67737 | Data Management Layer | Main Task | New | 4572700% | 4572900% | 24 | 0 | 0%
16224 | Create NeonDB Schema | Subtask | New | 4572700% | 4572700% | 2 | 0 | 0%
96271 | Integrate NeonDB into the application | Subtask | New | 4572700% | 4572700% | 1 | 0 | 0%
73376 | Implement Router for Data Fetching | Subtask | New | 4572700% | 4572700% | 5 | 0 | 0%
51169 | Implement Router for Data Inserting | Subtask | New | 4572800% | 4572800% | 8 | 0 | 0%
76036 | Implement Router for Data Updation | Subtask | New | 4572900% | 4572900% | 8 | 0 | 0%
91660 | Create Vercel Deployment Strategy | Main Task | New | 4573000% | 4573000% | 8 | 0 | 0%
31612 | Create Vercel Application and Host the App | Subtask | New | 4573000% | 4573000% | 3 | 0 | 0%
56860 | Create Env variables and manage secrets for Production | Subtask | New | 4573000% | 4573000% | 5 | 0 | 0%
10437 | Dashboard Page | Main Task | New | 4573100% | 4573100% | 8 | 0 | 0%
21603 | Use grid library for table (read-only) | Subtask | New | 4573100% | 4573100% | 8 | 0 | 0%
52373 | Make Dashboard Table Editable | Main Task | New | 4573200% | 4573300% | 16 | 0 | 0%
18933 | Make table editable by onclick | Subtask | New | 4573200% | 4573200% | 4 | 0 | 0%
33513 | Update the table record on enter/unfocus of cell | Subtask | New | 4573200% | 4573300% | 12 | 0 | 0%
66132 | Adding Application Page | Main Task | New | 4573400% | 4573600% | 24 | 0 | 0%
16670 | Create form component | Subtask | New | 4573400% | 4573400% | 8 | 0 | 0%
51316 | Add resume upload functionality | Subtask | New | 4573500% | 4573500% | 8 | 0 | 0%
67004 | Upload form data to DB | Subtask | New | 4573600% | 4573600% | 8 | 0 | 0%
17674 | Misc tasks & Final Release | Main Task | New | 4573700% | 4573800% | 16 | 0 | 0%
| Total |  |  |  |  | 224 | 8 | 3.571%

## Summary
Status | Count | Percentage
New | 0 | #DIV/0!
In Progress | 0 | #DIV/0!
Done | 0 | #DIV/0!
Total | 0